## Manual Chart
| Software Design and Technology | START DATE | END DATE | DURATION (WORK DAYS) | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10
[5 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Game Development
| Start game | 2020-06-12 | 2020-07-03 | 16 | bar: WEEK 7 T; WEEK 10 T; WEEK 10 Th
| Start logbook | 2020-06-29 | 2020-07-03 | 5 | bar: WEEK 7 T; WEEK 10 T; WEEK 10 Th
| collisions working | 2020-06-30 | 2020-07-03 | 4 | bar: WEEK 10 T
| asteroids falling randomly | 2020-07-03 | 2020-07-03 | 1 | bar: WEEK 10 T
| Gantt Chart | 2020-07-02 | 2020-07-03 | 2 | bar: WEEK 10 T
| Logbook | 2020-07-02 | 2020-07-03 | 2 | bar: WEEK 10 T
| Data Dictionary | 2020-07-02 | 2020-07-03 | 2 | bar: WEEK 10 T
| Storyboard | 2020-07-02 | 2020-07-03 | 2 | bar: WEEK 10 T
| Test report | 2020-07-02 | 2020-07-03 | 2 | bar: WEEK 10 T
| Design Specifications | 2020-07-02 | 2020-07-03 | 2 | bar: WEEK 10 T
| Evaluation of Solution | 2020-07-02 | 2020-07-03 | 2 | bar: WEEK 10 T
| Maintenance Projection | 2020-07-02 | 2020-07-03 | 2 | bar: WEEK 10 T
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])